## Flow Diagram
Complete Costco EDI Flow — Umpqua and Park City Plants
NOTE :
Park City Plants Fresno /Fairfield / Model -- Walmart /Sams and potentially Pitco use this same process
UMPQUA WALMART should be a direct AS2 connection

## Task List
Costco → Orderful Checklist
Plain task list — what needs to happen before we can turn off our current EDI VAN for Costco
UMPQUA
Complete | Activity | Type | Assigned To
☐ | 850 flat file → UMPQUA PLANT JSON mapping (build the actual working parser that outputs Orderful's exact field names — we have the mapping reference, not the finished code yet) | JSON MAPPING | Orderful
☐ | Orderful 856 manual label/send setup (portal-based — this is the interim process until Umpqua has a WMS) | Orderful Portal Setup | Orderful
☐ | 810 JSON mapping to Orderful | JSON MAPPING | Orderful
PARK CITY — 3 PLANTS (Fairfield, Model Dairy, Fresno)
Current state: 850 already works via direct download/import today — no change needed here.
☐ | Get the 850 from Park City to Orderful via Repositrak, using AS2 | Connection | Narvel Taylor
☐ | 856 setup for Fairfield & Model Dairy — Orderful manual portal (same style of setup as Umpqua's) | Orderful Portal Setup | Orderful
☐ | 856 for Fresno — this is WMS-automatic, not manual portal -- JSON MAPPING 856 Flat File | JSON MAPPING | Orderful
☐ | 810 — same format as Umpqua, already mapped (reuse, just confirm it fires correctly for these 3 plants) | (Same as Umpqua) | (Same as Umpqua)