## 10-27 Client Meeting
10/27 Meeting with Shehadey (Client)
# | Topic | Item | Owner | Due date | Status | Pre Call Notes | During Call notes
1 | Costco | Costco 10-digit SAP vendor number (e.g., 0010020513 - not the AP or buyer number). Costco uses it to identify SHF, set up VAN routing and open SPS testing. | Shehadey |  | Open | Send to Mark. Testing can't start without it. | 30255-plant identifier
2 | Costco | Costco 860 PO changes are rare (3 since May). | Shehadey |  | Open | Can we set up email notification only for the 860? | Yes email to Order Desk
3 | Costco | 820 = payment/remittance detail from Costco; 824 = error notice from Costco on our 810/856. Aptean shows no Costco 820s, and two 824s (9/29, 10/21). Does SHF receive Costco 820s today outside Aptean? If so, how? | Shehadey |  | Open | Costco does not test the 820; it is switched on after go-live. 824s come from Costco (never sent by SHF): 2 in production (9/29, 10/21) and 2 from Costco's test ID TST1COSTCOUSAXX (9/24). The 824 is part of Costco testing. | Payment processor is High Radius(new) - 820 and the 824 would be emailed to SHF AR department.
4 | Costco | Costco sends an 852 (sales/on-hand by warehouse) daily from ZZ/103391843VMI, and Aptean sends an identical copy back out to 01/103391843VMI. Who receives that copy (Park City Group?), and does ERMS use the 852 at all? | Shehadey |  | Open | Verified in Aptean raw data 10/26: inbound ISA sender ZZ/103391843VMI; outbound ISA receiver 01/103391843VMI, same content. How do VMI orders flow into ERMS?
5 | Costco | Does Costco have a hard deadline for certification or go-live? | Shehadey |  | Open | OA: Costco testing runs in SPS portal (810, 824, 850, 856, 860, 997). Starts once vendor # is in.
6 | Aptean | When does the Aptean contract end, and is there a planned shutoff date? | Shehadey |  | Open | Drives the cutover deadline.
7 | SFTP | BizLink to Concurrent SFTP (CouchDrop): when can Narvel connect once we send credentials? Can BizLink send to both Aptean and CouchDrop during parallel testing? Which IP addresses do we need to allow? | Shehadey (Adam + Narvel) |  | Open
8 | Specs | Send 3 Costco 810 flat files from ERMS (we can pull the matching X12 810s from Aptean). If values differ between the two, we will ask for the ERMS cross-reference table. | Shehadey |  | Open | Pairs show whether values pass straight through or are translated. Table only needed if they are translated.
9 | Specs | Send 3 Costco pipe-delimited 850 flat files (as ERMS received them) - we can pull the matching X12 850s from Aptean by PO number. | Shehadey |  | Open | Lets us confirm the 850 mapping field by field.
10 | Specs | Current-state flow doc (Umpqua/SPS, Park City) | Shehadey |  | Open
11 | Park City | Schedule a call with Orderful (Kelly) and ReposiTrak about sending a copy of Park City Costco 850s (and 852s) to Orderful over AS2. | Shehadey |  | Open | Why: Fairfield and Model need Costco 856s, which we plan to build in Orderful WebEDI. WebEDI needs the 850 in Orderful first, and those orders come from Park City today. | Adam email Reposi Trak
12 | Park City | WebEDI 856s for Fairfield/Model: who enters them at each plant, and how do we test before go-live? | Concurrent (Mark) + Adam |  | Open
13 | Other action items

## Agenda
Shehadey Foods — Next Call Agenda
Weekly call after the 10/20 working session · times are suggestions
# | Topic | Lead | Minutes | Notes
1 | Recap of 10/20 decisions | Mark | 3 | New Orderful ISA; Concurrent hosts SFTP; Park City stays as-is; Costco first.
2 | Costco certification and go-live date | Mark | 5 | Critical question.
3 | Costco 856 path: ReposiTrak AS2 + WebEDI for Park City plants; Umpqua 856 | Mark / Adam | 8 | Critical + High questions.
4 | Mapping review: 850/810/856 drafts and open questions | John | 15 | Walk the Costco mapping workbook; only the open/inferred rows.
5 | Cross-reference table and required fields | John | 5
6 | SFTP: folder structure and BizLink connection | John | 5 | Concurrent provides details; Adam/Narvel connect.
7 | Other open questions | Mark | 4
8 | Next steps and blockers | Mark | 5 | See tabs.
Total minutes
Questions open or follow-up
Critical still open
Answered

## Questions
Shehadey Foods — Questions
Open and follow-up questions first; answered questions (gray) at the bottom. Updated from the 10/20 call transcript.
# | Priority | Topic | Question | Context | Owner | Answer / notes | Status | 10/22 or after Mark notes
1 | Critical | Files | Can you send a Costco raw 850 and the flat file Aptean produced from it (Umpqua/SPS)? Or confirm we should pull both from Aptean ourselves. | Only Walmart/Sam's raw 850s were uploaded. A Costco pair takes the 850 mapping from ~89% to near 100%. | Adam | Mark to try pulling from Aptean first using the credentials in the Orderful credential vault. | Follow-up | Mark to follow up with Adam - log in saved in Orderful is not working
2 | Critical | Costco 856 (Park City plants) | Can Park City / ReposiTrak send a copy of the Costco 850 (or 852) to Orderful over AS2? | Without an 850 in Orderful, WebEDI can't build the 856 for Fairfield and Model. | Adam | Adam to contact Park City / ReposiTrak. | Follow-up | Adam emailed Kelly asking about how we could connecto to ReposiTrak via AS2. She requested a time to meet
3 | Critical | Costco go-live | What is the Costco certification status and target go-live date? | Certification target of 10/15 was missed; Costco sets go-live after certification. SPS costs $100/vendor/month and is growing. | Adam |  | Open
4 | Critical | Cross-reference | Can you send the ERMS cross-reference table (store/ship-to and item cross-references)? | Confirmed on the call that ERMS uses a cross-reference table (e.g., store 482). One miss drops the whole file. | Adam / Narvel |  | Open
5 | Critical | Specs | Is there an 'IN 810 file layout' document (and equivalents for the 850/856)? Your 810 template refers to it. | Would close several unknown header fields (810 HDR 14, 18, 19, 28; 856 HDR 13–18). | Adam |  | Open | Short question to Adam - are there any other flat file specs (810, 856, 850, 852) other than those provided?
6 | High | Doc type scope | Does ERMS import any of the 860, 876, 895, 820, 812, 864 or 824 today, or does Aptean just receive them? | Decides which of the 17 doc types in use need an ERMS mapping. 852 confirmed as no mapping (10/20). Likely no mapping: 997, 816; possibly 820/812/864/824 if AR can use Orderful's UI or alerts. | Adam / Narvel |  | Open
7 | High | Aptean | Does Aptean apply partner-specific logic or cross-references on top of the ERMS layout? | Adam: Aptean maps X12 to what ERMS needs; anything extra is ignored. Partner-specific rules not confirmed. | Adam | Partly answered; we'll check maps in Aptean. | Follow-up | Gain access and check maps in Aptean
8 | High | ERMS import | Which fields must be populated for ERMS to import (field level, not just record types)? | Adam: ERMS needs only the HDR/HST/HBT/HCM/LDT/TOT records; other data ignored. Field-level rules still unknown. | Adam | Record-level answer only. | Follow-up | Gain access and check maps in Aptean
9 | High | ERMS import | How should Tray handle an order missing required data: write the file anyway and let ERMS reject it, or hold it and alert? | ERMS drops the whole file on an error and failures are silent. | Adam / John |  | Open
10 | High | ERMS import | Does ERMS have a test environment, or a way to keep test 850s out of production? |  | Adam |  | Open
11 | High | 856 | For Umpqua Costco, will the 856 come from the RA program (no SSCC) or manual WebEDI? Costco requires SSCC labels. | Umpqua has no WMS; RA-style data can't show pallets or short ships. | Adam |  | Open
12 | High | 856 | Which flat file field is the true shipped quantity (HI 13 vs HI 14)? Where do ship-from, carrier, BOL and weight come from? | HI 14 is 0 in the UW sample; no source for N1*SF, TD5, REF*BM, TD1. | Adam |  | Open
13 | High | SFTP | Can BizLink send one file to two destinations (for comparing against Aptean during testing)? | Adam: BizLink is a file mover and supports many setups. | Adam |  | Open
14 | High | Costco pilot | Can you share the SPS testing portal credentials? | Kickoff action item. | Adam |  | Open
15 | High | Plant routing | Confirm how each partner identifies the plant in the 850 (DUNS, store number, buyer-vendor number). | Becky: DUNS identifies the location. Needed because all partners move to one Orderful ISA. | Adam / Becky |  | Follow-up
16 | Medium | Partners | When can we get the Mid Valley (Phase 2) partner list? |  | Becky |  | Open
17 | High | Doc types | Do the 820, 812, 864 and 824 need to go into ERMS, or is viewing them in Orderful enough? |  | Adam |  | Open
18 | Medium | Doc types | Where does the 855 come from today? |  | Adam |  | Open
19 | Medium | Files | What do the NCS and NCW file prefixes mean, and what naming must Tray use? |  | Adam |  | Open
20 | Medium | Aptean | What's the biggest frustration with Aptean today, and what does success look like? | Heard so far: Aptean portal is clunky, multiple ID sets are confusing, limited documentation since the iSeries/EDI lead retired, SPS cost growing. | Steve / Adam | Partly answered. | Follow-up
21 | Critical | SFTP | Who will own and host the SFTP server? |  | Adam / John | Concurrent hosts it ('way easier for us'). Concurrent provides inbound/outbound folders and instructions; Adam and Narvel connect BizLink (file mover only). John to confirm any added cost internally. | Answered
22 | Critical | File types | Will ERMS expect two 850 file types (Park City fixed-width and pipe-delimited)? |  | Adam | Park City orders are downloaded directly from Park City's site (not EDI) for Fresno, Fairfield and Model (VMI: Walmart, Sam's, Costco, maybe Pitco). Plan: leave Park City as-is, so Tray only builds the pipe-delimited (NCS/NCW) format. Umpqua trades direct via EDI. | Answered
23 | Critical | Specs + payloads | Can you send a spec for every document type plus related payloads? |  | Adam | Adam's mapping templates are the spec (no formal spec exists). Received: 850/810/856 templates, 59 production 850 flat files, 810 and 856 samples, Park City layouts (Costco 50A, Walmart 60A, Pitco), 6 raw Walmart/Sam's 850s. Aptean access provided to pull raw X12. | Answered
24 | Critical | Aptean vs ERMS | Are the Aptean mappings the same as the ERMS flat file mappings? |  | Adam | Aptean translates X12 into the ERMS flat file 'based on what you told us you need.' The flat file is what Tray must reproduce. Partner-specific logic: see follow-up above. | Answered
25 | High | Costco pilot | Which Costco relationships are in the pilot? |  | Adam | Two channels: (1) Umpqua via SPS: 850 in, 810 out, 856 in testing. (2) Park City VMI for Fresno/Fairfield/Model: 852 carbon copy to Park City, 850 by direct download, 856 now required. Fresno has a WMS; Fairfield (~10 Costcos, ~10/day) and Model manual via WebEDI; Umpqua 2 products about twice a week. | Answered
26 | High | ISA IDs | Keep plant-based ISA IDs or switch to new Orderful ISA IDs? |  | Adam | Switch to new Orderful ISA IDs for all partners (consolidates Umpqua, Producers and Mid Valley ID sets). Plant identified by DUNS / store in the 850. | Answered
27 | High | Working model | Who answers field-level questions while we map offline? |  | Adam | Adam (with Narvel). Concurrent maps offline, sends questions, reviews at the weekly meeting. | Answered
28 | High | ERMS import | How does ERMS identify the ship-to and bill-to? |  | Adam | By an ID that ERMS looks up in its cross-reference table; ERMS takes the bare minimum and does the rest. | Answered
29 | High | Costco pilot | How will Costco ASNs and labels be handled? |  | Adam | Fresno automated via WMS; Fairfield and Model manual via Orderful WebEDI (SCAC can be hardcoded to their own trucks). WMS for remaining plants targeted by end of next year. | Answered
30 | High | Partners | Is the partner list complete so we can mass upload? |  | Adam | Proceed: Mark pushes trade requests now with the new Orderful ISA, Costco first. A few partners still have questions. | Answered
31 | Medium | Doc types | Confirm the 852 carbon copy setup. |  | Adam / Narvel | ERMS does not process the 852 (Narvel confirmed). Orderful can accept it, return a 997, and optionally email a notice. | Answered
32 | Medium | Orderful | Status of historical data in the Orderful UI? |  | Adam | Uploaded to Orderful Historical Data as 3 zips (files renamed): Park City layouts, 59 flat files, 6 raw 850s. | Answered
33 | Medium | Background | What are parse_pipe_850.py / parse_pcg_fixed.py? |  | Adam | Adam's own Claude-built scripts (redactor + parser) used to build the mapping templates. | Answered

## Next Steps
Next Steps
From the 10/20 call. Fill in due dates.
Internal milestones (Concurrent)
# | Owner | Milestone | Target date | Status | Depends on
M1 | Michel | SFTP server stood up (sandbox first), BizLink connection guide sent. Use Couch for Shedhadey. IW to set up Couch | 2026-10-26 | Not started | SFTP hosting decision / cost (John)
M2 | Mauricio | First 850 brought from Orderful to the SFTP server in ERMS flat file format |  | Not started | M1; Costco trade request live in test; Costco raw 850 + flat file pair to confirm mapping
M3 | Michel + Mauricio | Tray flows ready for outbound (810, 856) from SFTP to Orderful, and test complete |  | Not started | M1; BizLink connected by Shehadey; Costco 810/856 sample files
M4 | Mark (+ Adam) | End-to-end UAT-ready data (Costco test orders through ERMS and back) |  | Not started | M2, M3; Costco test scenario in Orderful
M5 | Mark | Target go-live date (Costco) |  | Not started | Costco certification; M4 sign-off
M6 | Michel | IHM error-handling flows complete |  | Not started | Before M5
Next steps
# | Owner | Action | Due date | Status | 10/22 or after Mark Notes | Ask Claude
1 | Concurrent (Michel) | Stand up SFTP with inbound/outbound folders; send connection details and instructions |  | Open
2 | Concurrent (John) | Confirm SFTP hosting cost internally |  | Open
3 | Concurrent (Mark) | Push trade requests (mass upload) with new Orderful ISA, Costco first |  | In progress | 10/26: Costco trade request 220507 created via Orderful (Shehadey ORDFLSHEHAFOODS → Costco COSTCOEDIUSA; type New; outreach skipped; status Pending requirements). Mass upload for other partners still pending. 10/27 OA: setting up program, 5 guidelines, scenarios on 220507; authorization received; vendor # pending from Shehadey (needed before testing).
4 | Concurrent (Mark) | Log in to Aptean (credential vault) and pull Costco raw 850s matching the NCS flat files |  | In progress | Aptean credentails not working (URL seems wrong), must follow up with Adam
5 | Concurrent (Mark: project/epics · Michel: technical tickets) | Create Jira tracking: Mark sets up the project, epics per milestone, and PM tasks; Michel breaks the build into technical tickets and keeps them current |  | Open
6 | Concurrent (Michel) | Build IHM error-handling flows: alerts for failed translations, missing required fields, cross-reference misses, and files not picked up (ERMS fails silently today) |  | Open
7 | Concurrent (John + Claude) | Confirm inferred rows in the Costco mapping workbook against Costco pairs and Orderful guidelines; send questions to Adam |  | Open
8 | Concurrent (Mark) | Set up WebEDI for Costco 856s (Park City plants); hardcode SCAC |  | Open | How to test the Web EDI set up?
9 | Concurrent (Mark) | Configure 852 receipt with 997 (no ERMS file) in Orderful |  | Open | 10/26: 852 source ISA unclear (inventory shows 103391843VMI, not in Orderful). Asked Anu which Costco account sends 852s.
10 | Shehadey (Adam) | Contact Park City / ReposiTrak about an AS2 copy of the 850 (or 852) to Orderful |  | Open | Kelly asked for a meeting with Adam to scope this request
11 | Shehadey (Adam) | Create current-state document / flow chart: Umpqua-Costco-SPS path, Park City path, gaps |  | Open
12 | Shehadey (Adam) | Send the Park City translation document and the raw 850 behind the mapped flat file |  | Open
13 | Shehadey (Adam) | Send the ERMS cross-reference table and the 'IN 810 file layout' doc |  | Open
14 | Shehadey (Adam + Narvel) | Connect BizLink to the Concurrent SFTP once ready |  | Open
15 | Shehadey (Adam) | Confirm Costco certification status and go-live date |  | Open
16 | Orderful | Confirm support for UCS doc types, version 4030, and clearinghouse routing |  | Open
17 | Concurrent (Mark) | Forward Adam's 810/856 email (received) |  | Done
18 | Orderful (Anu) | Review trade request 220507 requirements; confirm the Costco scenario covers 850, 860, 810, 997; trigger outreach to Costco when ready |  | Open | 10/27: handled via Orderful Onboarding Agent (task 01a178b2). Costco testing in SPS portal covers 810/824/850/856/860/997; 820 untested, on after go-live.
19 | Orderful (Anu) | Confirm which Costco account sends the 852; add the 852 (accept + 997 only) to the right scenario or create a second trade request |  | Open
20 | Concurrent (Mark) | Create the COSTCOMASN (856) trade request once the Costco ASN approach is settled |  | Open | 10/27: asked Anu to create COSTCOMASN (856) and 103391843VMI (852) requests. OA confirms 856 step goes on COSTCOMASN.
21 | Concurrent (Michel + Mauricio) | Build Tray workflows — Inbound: Orderful 850 (JSON) → ERMS pipe-delimited flat file → SFTP inbound folder. Outbound: SFTP outbound 810/856 flat files → Orderful JSON → Orderful API. Shared: polling, batch splitting (HDR…TOT), archive and error folders |  | Open
22 | Concurrent (Mark + Anu) | Move the Costco 856 to COSTCOMASN: create the COSTCOMASN trade request; the 856 is currently on the 220507 (COSTCOEDIUSA) relationship |  | Open | 10/28: Michel should not treat the COSTCOEDIUSA 856 relationship as final.
23 | Concurrent (Mark) | Ask the Orderful Onboarding Agent to rebuild the Costco 810 Mosaic transformation against the current 810 guideline (240460); it was built from archived 218697 |  | Open | 10/28: found via MCP review of relationship 287882.

## Blockers
Blockers
What's holding the project up, and who clears it.
# | Blocker | Impact | Owner to clear | Target date | Status
1 | SFTP not yet provisioned | No BizLink connectivity or end-to-end testing | Concurrent (John) |  | Open
2 | No Costco raw 850 + matching flat file | 850 mapping can't be fully verified | Mark (Aptean) / Adam |  | Open
3 | No 850 in Orderful for Park City Costco orders | WebEDI can't build 856s for Fairfield/Model | Adam (ReposiTrak AS2) |  | Open
4 | Costco certification and go-live date unknown | Timeline can't be set | Adam |  | Open
5 | ERMS cross-reference table not received | Can't validate files before sending | Adam |  | Open
6 | Umpqua 856 lacks SSCC data | Automated Costco 856 may not pass | Adam |  | Open
7 | Field-level required fields unknown | Risk of ERMS silently dropping files | Adam |  | Open

## Spec Requirements
What a Usable Flat File Spec Must Include
Adam's mapping templates are being used as the spec; this checklist shows what's still missing.
# | Area | Requirement | Covered? (Y/N/Partial)
1 | Scope | One spec per document type and direction, per system | Y
2 | File structure | Record types, order, which repeat | Y
3 | File structure | Delimiter or fixed positions; line endings; encoding | Y
4 | File structure | One order per file or many | Y
5 | Fields | Every field by record and position, name, description | Partial
6 | Fields | Data type and length | Partial
7 | Fields | Required / optional / conditional | N
8 | Fields | Formats: dates, decimals, padding | Partial
9 | Fields | Valid code values | Partial
10 | Fields | Which fields ERMS checks against the cross-reference table | N
11 | Behavior | Error handling | Partial
12 | Behavior | How the plant is identified | Partial
13 | Behavior | Partner-specific variations | Partial
14 | Delivery | File naming and folders | Partial
15 | Samples | Raw EDI + matching flat file per document type | Partial

## Parked (Mapping Call)
Parked for the Mapping Call
Line-level questions now tracked in specs/<doc>/questions.md and the mapping workbook.
# | Question
1 | HDR 8–10, 12–20, 35–38 (850): unused?
2 | LDT 26 (850): what is the 0?
3 | UOM code list beyond CA/EA
4 | Allowance rate basis (per case vs per unit) from ERMS note table
5 | HCM: all partner notes and legal text into HCM?

## Internal Team Call
Shehadey Foods — Internal Team Call (Concurrent)
Mark (PM) · John Weathers (sales) · Michel (engineer) · Mauricio (dev). Goal: agree who builds what for the Costco go-live.
Agenda (30 min)
# | Topic | Lead | Notes | Notes | Notes | Mark Comments
1 | Where we are | Mark | Decisions from 10/20: Concurrent hosts SFTP, new Orderful ISA, Park City stays as-is, Costco first. Mapping drafts: 850 89%, 810 86%, 856 75%. |  |  | Completed last call
2 | Commercial check | John | SFTP hosting cost; scope vs priced doc types (17 in use vs ~7 priced); Park City out of scope; WebEDI is manual for Fairfield/Model.
3 | Build plan and estimates | Michel / Mauricio | Tray workflows, SFTP, and the three Costco maps. What can be ready for Costco go-live?
4 | Blockers we can clear ourselves | Mark | Aptean login, ReposiTrak meeting, WebEDI test approach.
5 | Owners and dates | Mark | Fill in the table below.
Internal next steps
# | Owner | Action | Why / input | Due | Status | Mark Comments
1 | Michel | Stand up Concurrent-hosted SFTP (sandbox first): inbound/outbound folders, per-plant or per-doc-type layout, SSH key or password, IP allowlist | Client connects with BizLink (file mover only) |  | Open
2 | Michel | Write a one-page BizLink connection guide for Shehadey (host, folders, naming, pickup/archive rules) | Client asked us to tell them the folder structure |  | Open
3 | Michel | Design the Tray flows: Orderful API → 850 flat file → SFTP; SFTP → 810/856 flat file → Orderful API | See integration flow page |  | Open | Mark to Share RC Moore Tray Work Space
4 | Michel | Design error handling and alerts: ERMS drops a whole file on one bad record and fails silently. | Decide: hold and alert, or write and let ERMS reject |  | Open | Is this a client question?
5 | Mauricio | Build the 850 writer (Orderful 850 JSON → ERMS pipe file: HDR/HST/HBT/HCM/HAL/LDT/LAL/TOT) | outputs/2026-10-21-costco-mapping-workbook.xlsx, 850 tab |  | Open
6 | Mauricio | Build the 810 and 856 parsers: split multi-invoice batches (HDR…TOT); group 856 pallets by HI field 26 | 810 and 856 tabs; client templates in specs/810 and specs/856 |  | Open
7 | Mauricio | Test against real samples: 59 850 flat files, EDITESTredacted.810, EDI_UW.856, EDI_RA_redacted.856 | specs/*/samples in the repo |  | Open
8 | Michel + Mauricio | Review inferred (🟡) and open (❓) rows; send one consolidated question list to Adam via Mark | specs/*/questions.md |  | Open
9 | Mark | Fix Aptean access with Adam (saved URL/login not working); pull a Costco raw 850 + matching flat file | Turns 850 inferred rows into verified |  | Open
10 | Mark | Join Kelly/Adam meeting on ReposiTrak AS2 (Park City Costco 850s into Orderful) | Needed for WebEDI 856s at Fairfield/Model |  | Open
11 | Mark | Confirm with Orderful how to test the WebEDI 856 setup for Costco | Mark's note on Next Steps |  | Open
12 | Mark | Push trade requests (new Orderful ISA, Costco first) |  |  | Open
13 | John | Confirm SFTP hosting cost and whether it changes the quote | Client prefers Concurrent-hosted |  | Open
14 | John | Check scope vs contract: doc types priced vs in use; Umpqua 856 approach (RA has no SSCC) | Avoid unpriced work |  | Open
15 | Team | Agree a Costco target date to give the client, once certification date is known | Costco sets go-live after certification |  | Open
16 | John | Pull the signed Orderful/Concurrent order form or SOW and confirm what's priced: one-time fee per partner, ongoing subscription per partner, per-doc-type fees, Concurrent onboarding services, and the $5,500/doc type Tray build | Intake brief only names $5,500/doc type, VAN 3¢/transaction, $5,400/mo year-4 renewal at 45 partners, 3-year ramp. Per-partner fees aren't spelled out anywhere we've seen. |  | Open
17 | John | Confirm which doc types are in the signed scope (sales list: 850, 875, 880, 810, 856, 855, 945). 945 isn't in the client inventory; 894 is used by 3 partners but isn't on the sales list | Questions tab |  | Open
18 | Mark + Michel | Set up Jira tracking (Mark: project, epics per milestone, PM tasks; Michel: technical build tickets) | Milestones on the Next Steps tab |  | Open
Risks to discuss
— | Costco go-live may come fast after certification; SPS cost (~$300–400/month) adds pressure

## Internal Call Agenda 10-27
Internal Call Agenda 10/27 (Concurrent)
Prep before the client call with Adam.
# | Topic | Item | Owner | Due date | Status | Notes
1 | Trade requests | 220507 (COSTCOEDIUSA): Orderful agent waiting on vendor # + authorization | Concurrent (Mark) |  | In progress | 10/27 OA: planning setup now (program, guidelines, scenarios); approval buttons post in thread. Vendor # can come later. 10/27 11:30: 220507 now ACCEPTED - relationships 850, 860, 820, 824 in; 810, 856 out. 856 was added here too (OA said COSTCOMASN) - confirm. Shehadey-side relationship setup pending (Mosaic goes here).
2 | Trade requests | COSTCOMASN (856) and 103391843VMI (852) requests - status | Concurrent (Anu) |  | Open | OA: scenario 856 step goes on COSTCOMASN (26671), not 220507.
3 | New finding | 852 runs both ways (in and out daily) - design impact? | Concurrent (Michel) |  | Open
4 | New finding | 103391843PCG: ~50 810s/day not in plan - scope and phase? | Concurrent (John + Mark) |  | Open
5 | New finding | 860 rare, no 820/824 seen - keep in scope? | Concurrent (Mark) |  | Open | OA: 820 has no Costco test - set up, switch on after go-live. 824 and 860 are in testing.
6 | Mosaic | Poller channel on Shehadey account; Mosaic on all relationships | Concurrent (Michel) |  | Open
7 | Mosaic | 820/824 have no Mosaic schema - adapter handles standard JSON? | Concurrent (Michel + Mauricio) |  | Open
8 | SFTP | CouchDrop account setup status (M1) | Concurrent (Michel) |  | Open
9 | Build | V3 adapter design and flat file mapping status | Concurrent (Michel + Mauricio) |  | Open
10 | Testing | Costco scenarios: Produce/Meat set (99238, 99245, 99240) - agree? | Concurrent (Mark + Anu) |  | Open | OA recommends Produce/Meat set. SPS judges results in its portal.
11 | Park City | WebEDI 856 approach for Fairfield/Model | Concurrent (Mark) |  | Open
12 | Commercial | Per-TP fees / scope change for new flows | Concurrent (John) |  | Open
13 | Tracking | Jira project and epics set up | Concurrent (Mark + Michel) |  | Open
14 | Client call | Who covers which items with Adam | Concurrent (Mark) |  | Open
15 | Trade requests | Verify real ISA IDs: PCG 810 header shows ISA 01/103391843 with GS 103391843PCG. Is VMI the same (GS only)? Hold Anu's 103391843VMI request until confirmed. | Concurrent (Mark + Anu) |  | Done | 10/27: VMI confirmed real ISA (inbound ZZ/103391843VMI, outbound 01/103391843VMI). PCG is GS-only on ISA 01/103391843 (Costco account 2499). OK for Anu to proceed on VMI.