## Agenda
Shehadey Foods — Call Agenda
Concurrent-led Orderful onboarding · Times are suggestions
# | Topic | Lead | Minutes | Notes
1 | Recap and today's goals | Mark | 2 | Kickoff decisions: Costco pilot, ~45 partners, ~6-month rollout.
2 | Who owns the SFTP server | John | 6 | Critical Q1.
3 | One 850 file type or two (Park City vs pipe-delimited) | John | 5 | Critical Q2.
4 | Specs for every document type + related payloads | John | 8 | Critical Q3. Walk through the Spec Requirements tab.
5 | ERMS cross-reference file | John | 3 | Critical Q4.
6 | Aptean mappings vs ERMS flat file mappings | John | 4 | Critical Q5.
7 | Costco go-live date, pilot scope and ISA IDs | Mark | 7 | High Q6–9.
8 | Other open questions (as time allows) | Mark | 5 | Remaining High/Medium questions.
9 | Next steps, owners and blockers | Mark | 5 | See Next Steps and Blockers tabs.
| Total minutes |  | 45
Goals for the call
• SFTP owner decided (or decision date set); BizLink contact named
• Confirmed whether Tray builds one 850 format or two
• Dates committed for a spec + related payloads for every document type
• Cross-reference file requested with a date
• Answer on whether Aptean adds logic beyond the ERMS layout
• Costco go-live date and ISA approach agreed (or owner + date to decide)
| Open questions |  | 24
| Critical questions still open |  | 5

## Questions
Shehadey Foods — Questions for Today's Call
5 critical questions first (red), then High and Medium. Yellow cells are for notes during the call. Status: Open / Answered / Follow-up.
# | Priority | Topic | Question for Shehadey | Why it matters / context | Shehadey owner | Answer / notes | Status
1 | Critical | SFTP | Who will own and host the SFTP server: Shehadey or Concurrent? (John is weighing cost, setup and upkeep.) Either way: who is your BizLink admin, and what are BizLink's IPs, preferred login (key or password), folder layout per plant, and file naming? | Both options were raised at kickoff. Nothing can connect or be tested end to end until this is settled. |  |  | Open | Yes Concurrent will provide this
2 | Critical | File types | Will ERMS expect two 850 file types going forward (Park City fixed-width and pipe-delimited), or only the pipe-delimited format once Orderful delivers Costco/Walmart/other partners directly? Will Park City Group keep sending its fixed-width files on its own, outside Orderful? | Two inbound formats today: pipe-delimited (NCS/NCW) and Park City fixed-width (PRODUCERS_ORDERS). Determines whether Tray must build one format or two. |  |  | Open | Yes they will have 2 different flat file types
3 | Critical | Specs + payloads | Can you send an actual spec for every EDI document type (850, 810, 855, 856, 852, 880/894 and any others), meeting the requirements on the 'Spec Requirements' tab? For each, also send related payloads: the raw EDI and the matching flat file for the same transaction (850, 856, 810 first; Costco examples preferred). | The 850 Word doc is research, not a complete spec. It references an 'original 850 layout doc' and Park City layout docs (Walmart 60A, Costco 50A, Pitco); ask for those originals too. |  |  | Open | Adam will either send mutiple files or will provide Concurrent direct access to APTEAN
4 | Critical | Cross-reference | Can you send the ERMS cross-reference file? Which values does ERMS check against it (item numbers, UPCs, store/ship-to IDs)? | The spec defines the file's structure; the cross-reference file is ERMS master data that translates partner codes into ERMS codes. One miss drops the whole file, so Tray needs it to validate before sending. |  |  | Open | No cross reference file is available
5 | Critical | Aptean vs ERMS | Are the Aptean mappings the same as the ERMS flat file mappings? Does Aptean apply partner-specific logic or cross-references on top of the ERMS layout, and can those maps be exported? | The ERMS-side flat file stays the same after cutover; Tray replaces Aptean as its producer. Any logic Aptean adds per partner has to be rebuilt in Tray. |  |  | Open | Yes they are the same (confirm via the transcript)
6 | High | Costco pilot | What is the target go-live date for Costco? | Drives the whole timeline. Aptean shut-off estimate is Jan/Feb 2027 and overlap cost is a known concern. |  |  | Open | ASAP
7 | High | Costco pilot | Which Costco relationships are in the pilot? (SPS 850/860/810, ASN 856, VMI 852, Park City Group) | Client inventory shows 4 separate Costco relationships under different plant IDs. |  |  | Open
8 | High | ISA IDs / plant routing | Do we keep the current plant-based ISA IDs (PRODNCS, UMPQUA, PRODDAIR, PRODUCENCS) or switch to new Orderful ISA IDs? If new, one per plant or one total? | Kickoff notes say 'net new Orderful ISA IDs.' But today the receiver ID is often how an order is routed to a plant (e.g., Walmart orders to Umpqua's ID vs PRODDAIR). The 850 rarely carries the plant itself. |  |  | Open | Use Orderfuls
9 | High | ISA IDs / plant routing | How does ERMS know which plant an 850 is for today: receiver ID, file name prefix (NCS vs NCW), import folder, or something else? | Mark's read: plant is sometimes passed on the 850 as a code. Need to see real payloads. |  |  | Open | Duns number
10 | High | Working model | Who on your side answers field-level questions while we map offline, and how quickly can they turn them around? | Plan: Concurrent maps and tests offline, then brings back only questions. |  |  | Open | Adam
11 | High | ERMS import | Which ERMS fields are mandatory for an import to succeed? | ERMS drops the whole file on an error. Should be covered by the spec (see Spec Requirements). |  |  | Open | Pending -
12 | High | ERMS import | How does ERMS identify the ship-to and bill-to? Is the ID alone enough? | Ship-to/bill-to layout varies by account (name present, name blank, or only an ID). |  |  | Open | HDR - TOT are the mandatory fields, anything else is dropped.
13 | High | ERMS import | Does ERMS have a test environment, or a way to keep test 850s out of production? | Avoid test orders becoming real orders. |  |  | Open
14 | High | SFTP | Can BizLink send one file to two destinations, so we can compare our output against Aptean's? | Enables low-risk parallel testing. |  |  | Open
15 | High | Costco pilot | How will Costco ASNs (pallet/SSCC data) and labels be handled? | Most ERMS 856s lack pallet data; Costco requires accurate ASNs. |  |  | Open
16 | High | Costco pilot | Can you share the SPS testing portal credentials? | Kickoff action item for the client. |  |  | Open
17 | High | Partners | Is the partner list complete so we can mass upload? Are Walgreens and Saladinos still active? | Mark uploads once the list is confirmed. |  |  | Open
18 | Medium | Partners | When can we get the Mid Valley (Phase 2) partner list? | Not in the current inventory. |  |  | Open
19 | Medium | Aptean | What's the biggest frustration with Aptean today, and what does success look like for you? | Docs point to cost (~$8K/mo), confusing kilo-character billing, two EDI setups, weak error visibility. Confirm in their words. |  |  | Open
20 | Medium | Doc types | Do the 820, 812, 864 and 824 need to go into ERMS, or is viewing them in Orderful enough? | All inbound, finance/AR-related. Affects build scope. |  |  | Open
21 | Medium | Doc types | Where does the 855 come from today? | Origin unclear in the intake brief. |  |  | Open
22 | Medium | Doc types | Confirm the 852 carbon copy to Park City Group setup. | From kickoff notes. |  |  | Open
23 | Medium | Orderful | Status of importing historical data in the Orderful UI? | Orderful asked the client to do this. |  |  | Open
24 | Medium | Background | What are parse_pipe_850.py / parse_pcg_fixed.py used for? Is your team building any part of the integration? | Named in the 850 doc's intro as the source of its JSON field names. |  |  | Open
Need to map for a single plant.
Repositrack AS2

## Spec Requirements
What a Usable Flat File Spec Must Include
Send to Shehadey with the spec request. One spec per document type; related payloads for each.
# | Area | Requirement | Included? (Y/N)
1 | Scope | One spec per document type and direction (e.g., 850 inbound, 810 outbound), per system (ERMS; later AX/Gentran)
2 | File structure | Record types and the order they appear (e.g., HDR, HST, HBT, HCM, HAL, LDT, LAL, TOT), and which repeat
3 | File structure | Delimiter (pipe) or fixed-width positions; line endings; character encoding
4 | File structure | One order per file or many; how one order/invoice/shipment is grouped
5 | Fields | Every field listed by record and position: field number (or start/end position), name, description
6 | Fields | Data type and length (min/max) for each field
7 | Fields | Required, optional or conditional (and the condition) for each field
8 | Fields | Formats: dates, times, decimals (implied or explicit), padding and justification, leading zeros
9 | Fields | Valid code values (units of measure, qualifiers, allowance/charge codes) with meanings
10 | Fields | Which fields ERMS checks against the cross-reference file
11 | Behavior | How ERMS handles errors (e.g., whole file dropped on a cross-reference error) and where errors are reported
12 | Behavior | How the plant is identified (receiver ID, file prefix, folder, or a field)
13 | Behavior | Any partner-specific variations of the layout
14 | Delivery | File naming convention and folder (per plant / per document type)
15 | Samples | Related payloads: the raw EDI and the matching flat file for the same transaction, for each document type and each format

## Next Steps
Next Steps
Fill in due dates and status during the call.
# | Owner | Action | Due date | Status
1 | Shehadey | Send a spec for every document type (per Spec Requirements tab), incl. original ERMS and Park City layout docs |  | Open
2 | Shehadey | Send related payloads (raw EDI + matching flat file) for each document type: 850, 856, 810 first, Costco examples preferred |  | Open
3 | Shehadey | Send the ERMS cross-reference file |  | Open
4 | Shehadey | Confirm whether Aptean applies partner-specific logic; export Aptean maps if possible |  | Open
5 | Shehadey | Name the field-question contact and BizLink admin; send BizLink IPs, login preference, folder layout |  | Open
6 | Shehadey | Share SPS testing portal credentials |  | Open
7 | Shehadey | Confirm partner list is complete; send Mid Valley list |  | Open
8 | Concurrent (John) | Decide SFTP host (Shehadey vs Concurrent), including any added cost |  | Open
9 | Concurrent (John + Claude) | Offline mapping: review specs and payloads, draft maps, test, list questions for Shehadey |  | Open
10 | Concurrent (Mark) | Send recap email with owners and dates within 24 hours |  | Open
11 | Concurrent (Mark) | Confirm mass-upload process with Orderful (Priya); upload partners once list is confirmed |  | Open
12 | Concurrent (Mark) | Update Asana, the project repo, and the weekly meeting invite |  | Open
13 | Orderful | Recommend ISA approach that preserves plant routing (per-plant IDs vs single ID) |  | Open
14 | Orderful | Confirm support for UCS doc types, version 4030, and the shared clearinghouse routing |  | Open
15 | Orderful | Confirm or walk back the former sales rep's commitments (9-day partner go-live, pricing, 997s) |  | Open

## Blockers
Blockers
What's holding the project up, and who clears it.
# | Blocker | Impact | Owner to clear | Target date | Status
1 | SFTP owner undecided | No BizLink connectivity, so no end-to-end testing | Concurrent (John) |  | Open
2 | Unclear whether Tray builds one 850 format or two | Can't scope or start the inbound build | Shehadey |  | Open
3 | Specs and related payloads not received | No mapping can start for any document type | Shehadey |  | Open
4 | ERMS cross-reference file not received | Can't validate files before sending; risk of ERMS dropping whole files | Shehadey |  | Open
5 | Unknown whether Aptean adds partner-specific logic | Hidden logic could be missed in the Tray build | Shehadey |  | Open
6 | ISA ID / plant routing undecided | Can't configure Orderful relationships or Costco trade requests; risk of orders reaching the wrong plant | Shehadey + Orderful |  | Open
7 | Costco go-live date and pilot scope not set | Can't build the timeline or prioritize mapping | Shehadey |  | Open
8 | Partner list not confirmed complete | Mass upload to Orderful on hold | Shehadey |  | Open

## Parked (Mapping Call)
Parked for the Mapping Call
Line-level questions. Not for today; Concurrent will raise only those still open after offline mapping.
# | Question
1 | HDR fields 21/22 and 34: what are they, and does ERMS use them?
2 | TOT (totals) record is always empty. Does ERMS still need the line present?
3 | LDT field 2: vendor item number or UPC? Does it vary by partner? Field 5 vs field 25 descriptions?
4 | Unit of measure: is it only CA = cases, everything else = eaches?
5 | Allowance/charge codes (I410, C110): the only ones ERMS acts on? Pass others through?
6 | HCM comments: should all partner notes and legal text go into HCM?